## Chart
Project Name
Iteration Name |  | 2013-11-12 | to | 2013-11-25
Burn-up Target (pts) | 33

## Input
Title | Project Name |  |  |  |  | Enter values in the Green Cells only.
Iteration Name |  | 2013-11-12 | 2013-11-25
|  | 2013-11-12 | 2013-11-13 | 2013-11-14 | 2013-11-15 | 2013-11-18 | 2013-11-19 | 2013-11-20 | 2013-11-21 | 2013-11-22 | 2013-11-25 | <==
| Burn-up Target (pts) | 0 | 3.6667 | 7.3333 | 11 | 14.6667 | 18.3333 | 22 | 25.6667 | 29.3333 | 33
| Actual Burn-up(pts.) | 0 | 3 | 9 | 12 | 12
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
BurnDown (hrs) | Todo (hrs) | 1: 142; 2: 128; 3: 0; 4: 0; 5: 0
| Doing (hrs) | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0
| Outstanding (hrs) | 1: 142; 2: 128
| Forecast Burndown | 142 | 128 | 114 | 100 | 86 | 72 | 58 | 44 | 30 | 16 | <==
Available Capacity |  | 159 | 141 | 123 | 105 | 93 | 81 | 63 | 45 | 27 | 9
Daily Ideal Hours |  | 18 | 18 | 18 | 12 | 12 | 18 | 18 | 18 | 18 | 9
Ideal Day | 6 | 1: hrs
Ideal Man Days |  | 3 | 3 | 3 | 2 | 2 | 3 | 3 | 3 | 3 | 1.5
|  | 2013-11-12 | 2013-11-13 | 2013-11-14 | 2013-11-15 | 2013-11-18 | 2013-11-19 | 2013-11-20 | 2013-11-21 | 2013-11-22 | 2013-11-25
Team |  | 2013-11-12 | 2013-11-13 | 2013-11-14 | 2013-11-15 | 2013-11-18 | 2013-11-19 | 2013-11-20 | 2013-11-21 | 2013-11-22 | 2013-11-25
1 | Bill | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5
2 | Joe | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5
3 | Bob | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 0.5
4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Product Owner |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Scrum Master |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Analyst/Architect |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on B8: The total unstarted work from the board in man hours Manually captured each day
Note on B16: A Ideal Man day (Reduce if need be , but increase at your peril)
Note on A14: Available Capacity until the end of the iteration in Man hours (Auto calculated)
Note on A17: Ideal Man Days available to do work for this day.
Note on B5: Actual points burnup manually captured (do not use Zero to clear cells, use Delete)
Note on B9: The total in progress work from the board in man hours Manually captured each day
Note on L4: Iteration target in Story Points
Note on C2: Capture Iteration Start Date here (Don't forget about the Project Name and Iteration Name
Note on A20: Availability (Days) If you want availability in hours, use hours in the table and set the Ideal Day to 1
Note on M3: Fiddle with the calculations in this row depending on what day your iteration starts on. (Columns D to L) In other words make sure that the dates correspond with your working days (check row 19 below to help)
Note on M11: The F'Cast burndown will contain a #DIV0 error until you have at least 2 days worth of burndown (Safe to ignore)
Note on C21: Availability (Days)

## Instructions
Start of Iteration (after planning)
1 | Archive the previous iterations workbook
2 | Capture your ideal day in hours in B16 (No more than 6)
3 | Input the Project Name in 'B2'
4 | The Iteration Title in 'A2'
5 | Iteration Start Date 'C2'
6 | Iteration Target Points in 'L4'
7 | Confirn that the days of the Week in row 19 and
8 | Dates for the iteration in row 3 Are what you expect
9 | If they are out, then amend the formula in D3 to L3 as needed
10 | Clear any Points Burn-up in row 5
11 | Clear any hours work remaining from rows 8 & 9
12 | Capture team names and availability in days in B21 to B30
13 | Capture the work remaining (estimated hours in tasks) in C8 & C9 (you will receive a #DIV0 error until you have at least 2 days worth of hours remaining captured. It is OK to ignore the error)
Daily
1 | Update any points Burn-up in row 5
2 | Update any work remaining in rows 8 and 9
3 | Save the workbook
4 | Print the Chart tab, making sure that a cell is selected and not the chart.
What the chart tells you
1 | Burn-up Target (pts.) - This is the Ideal burnup Target across the iteration. If you are below the line you may be in trouble with the amount of work committed to and unlikely to complete it all. If you are above the line, enjoy the feeling, it is unlikely to last long.
2 | Actual (pts.) - Actual points burn-up of 'Done' stories.
3 | Outstanding - the number of hours of outstanding work in the iteration
4 | Available Capacity - the available capacity of the team in hours for the rest of the iteration
5 | F'cast - A prediction on how hours of work outstanding are expected to burn-down across the rest of the iteration. If it stays below the Available capacity, you are ok, if is goes above then you are likely to run out of time based on current progress.